## Bug Report
Defect ID | Type | Summary | Description | Status | Severity | Priority | Test Environment | Test Case Name | Release Name | Reported By
OC-001 | Bug | Sept 2023¦SIT 1¦ V_1.0¦ (https://demo.opencart.com)¦'Thank You For Registering' (confirmation email) Email is not sent to the registered email. | After registration confirmation mail is not sent to the registered email. Steps To Reproduce 1.From My Account go to Register page 2. Provide all mandatory details. 3. Cliclk 'Continue' Expected Result: 1. Confirmation mail should be sent to the registered e-mail after registration. Actual Result:registered e-mail after registration is not sent to the registered email. | Open | Minor | Low | SIT 1¦Browser- Google Chrome | TC_RF_04 | alpha1.0 | Swati
OC-002 | Bug | Sept 2023¦SIT 1¦ V_1.0¦ (https://demo.opencart.com)¦ Recipient's Name field accepts numbers, special characters and form is accepted and Thank you for purchasing a gift certificate! is shown. | Recipient's Name field accepts numbers, special characters and form is accepted and Thank you for purchasing a gift certificate! is shown. Steps To Reproduce 1. View Footer menu From 'My Account' Page. 2. Click on 'Gift Certificate' under the 'Extras' section. 3. Enter all the mandatory details and click 'Continue' Expected Result:1. Recipient's Name field should not accepts digits and special characters 2. error message should be shown "Recipient's Name has invalid formats!" Actual Result: Form should not be accepted. | Open | Major | Medium | SIT 1¦Browser- Google Chrome | TC_SC_005 | alpha1.0 | Swati
OC-003 | Bug | Sept 2023¦SIT 1¦ V_1.0¦ (https://demo.opencart.com)¦Message field accepts letters with spaces between each characters and form is submitted and Thank you for purchasing a gift certificate! is shown. | Message field accepts letters with spaces between each characters Steps To Reproduce 1. View Footer menu From 'My Account' Page. 2. Click on 'Gift Certificate' under the 'Extras' section. 3. Enter all the mandatory details and click 'Continue' Expected Result: 1. Message field should not aceept spaces between each character. Actual Result: Form is submitted and Thank you for purchasing a gift certificate! is opened. | Open | Major | Medium | SIT 1¦Browser- Google Chrome | TC_SC_012 | alpha1.0 | Swati
OC-004 | Bug | Sept 2023¦SIT 1¦ V_1.0¦ (https://demo.opencart.com)¦Shopping Cart¦Clicking cross sign in quantity column does not remove the item from Shopping Cart | Message field accepts letters with spaces between each characters Steps To Reproduce 1.From My Account>Click LogIn. Provicredentials>add any 2item in cart 2. Click Shopping Cart> Click Cross sign. Expected Result: 1. Item should be removed from the cart Actual Result: Item does not remove from the cart | Open | Critical | High | SIT 1¦Browser- Google Chrome | TC_SC_008 | alpha1.0 | Swati
OC-005 | Bug | Sept 2023¦SIT 1¦ V_1.0¦ (https://demo.opencart.com)¦Shopping Cart¦Estimate shipping & taxes¦Post code accepts special characters and alphabates and able to submit form. | Message field accepts letters with spaces between each characters Steps To Reproduce 1.From My Account>Click LogIn. Provicredentials>add any 2item in cart 2. Click Shopping Cart> Click Cross sign. Expected Result: 1. Post code should not accepts special characters and alphabates and form should not able to submitted. Actual Result: Post codeis accepting special characters and alphabates. 2. User is able to submit the form. | Open | Major | Medium | SIT 1¦Browser- Google Chrome | TC_SC_016 | alpha1.0 | Swati
OC-006 | Bug | Sept 2023¦SIT 1¦ V_1.0¦ (https://demo.opencart.com)¦Phone Number in header section should be in a valid format | Phone number is not in a valid format Steps To Reproduce 1.https://demo.opencart.com and open the application. Expected Result: 1. Phone Number should be in 10 digits Actual Result: Phone Number in header section should be in a valid format | Open | Minor | Low | SIT 1¦Browser- Google Chrome | TC_RF_18 | alpha1.0 | Swati